| UMass Medical Library IT Infrastructure Modernization Proposal | Project Overview LANZAR proposes modernizing the UMass Medical Library's technology infrastructure by designing and implementing a secure, reliable network with centralized file management and cloud-integrated storage. The project will leverage the library's existing hardware wherever practical while evaluating the need for a dedicated server or workstation-class system to provide efficient file sharing, user management, and long-term scalability. The implementation will include network configuration, secure cloud storage integration, data migration, backup and recovery planning, and comprehensive system documentation. The goal is to create a stable, secure, and easily managed IT environment that supports the library's daily operations while providing a foundation for future growth and ongoing technology needs. Jon Scott Prepared for: Beth |
| --- | --- |

Table of Contents

Objectives	2

Current Environment	2

Proposed Solution	2

Project Scope	3

Phase 1 – Infrastructure Assessment	3

Phase 2 – Network Deployment	3

Phase 3 – Server Deployment	3

Option A – Small Business Server	3

Option B – Workstation-Class Server	4

Phase 4 – Cloud Storage Integration	4

Phase 5 – Security	4

Phase 6 – Backup & Recovery	5

Phase 7 – Documentation & Training	5

Estimated Timeline	5

Deliverables	6

Optional Managed IT Services	6

Assumptions	6

Pricing	6

Why LANZAR	7

Acceptance	8

# Objectives

The goals of this project are to:

- Modernize the existing network infrastructure

- Centralize file storage and access

- Improve system security and reliability

- Simplify user and device management

- Implement automated backup and disaster recovery

- Create a scalable infrastructure for future growth

- Provide documentation and staff guidance

## Current Environment

Based on our initial discussions, the library currently has:

- Existing workstation hardware

- Existing networking equipment

- A need for centralized file storage

- Interest in cloud-based storage solutions

- A desire for improved network performance and management

A complete assessment will be performed prior to implementation to verify hardware compatibility, infrastructure requirements, and project scope.

## Proposed Solution

LANZAR recommends implementing a modern network environment consisting of:

- Centralized network management

- Secure business-grade firewall/router

- Managed network switching

- Dedicated server platform (or workstation-class solution based on assessment)

- Cloud-integrated file storage

- Automated backup systems

- Secure user authentication and permissions

# Project Scope

## Phase 1 – Infrastructure Assessment

- Inventory existing hardware

- Evaluate current network

- Review cabling and switching

- Assess Internet connectivity

- Document existing environment

- Identify security improvements

Deliverable

- Infrastructure Assessment Report

## Phase 2 – Network Deployment

Configure and deploy:

- Router / Firewall

- Managed Switch

- DHCP

- DNS

- Static addressing (where required)

- Secure Wi-Fi

- VLANs (if appropriate)

## Phase 3 – Server Deployment

Following the assessment, LANZAR will recommend the most appropriate solution.

### Option A – Small Business Server

Recommended if:

- Multiple staff users

- Long-term growth

- Increased reliability required

- Centralized services

Potential hardware examples:

- Dell PowerEdge T160

- Lenovo ThinkSystem

- HPE ProLiant

Benefits:

- Enterprise reliability

- ECC Memory

- RAID storage

- Future scalability

- Better uptime

### Option B – Workstation-Class Server

Appropriate if:

- Small user count

- Primarily file storage

- Budget-conscious deployment

Typical specifications:

- Intel Core i7/i9

- 32–64 GB RAM

- NVMe SSD storage

- RAID storage

- Windows Server or Linux

# Phase 4 – Cloud Storage Integration

Configure cloud synchronization using the platform best suited to the library's needs.

Potential providers include:

- Microsoft OneDrive / SharePoint

- Google Workspace

- Dropbox Business

- Wasabi Cloud Storage

Features include:

- Automatic synchronization

- File version history

- Secure remote access

- Off-site redundancy

- Disaster recovery support

# Phase 5 – Security

Implementation includes:

- User account management

- Group permissions

- Multi-Factor Authentication (where applicable)

- Firewall configuration

- Endpoint protection

- Automatic updates

- Security best practices

# Phase 6 – Backup & Recovery

Implement a backup strategy following the 3-2-1 Backup Rule.

- Primary server storage

- Local backup

- Encrypted cloud backup

# Phase 7 – Documentation & Training

Deliverables include:

- Network diagram

- Device inventory

- IP address documentation

- Administrative credentials

- Backup procedures

- Recovery documentation

- Basic staff orientation

# Estimated Timeline

| Phase | Estimated Time |  |
| --- | --- | --- |
| Assessment | 1 Day |  |
| Network Deployment | 1–2 Days |  |
| Server Configuration | 1 Day |  |
| Data Migration | 1–3 Days |  |
| Testing & Validation | 1 Day |
| Documentation & Training | 1 Day |

Estimated Total Duration: 5–8 Business Days

# Deliverables

Upon completion, the library will receive:

- Modern network infrastructure

- Centralized file storage

- Cloud-integrated backup system

- Secure user management

- Fully configured server

- Backup and disaster recovery solution

- Complete documentation package

- Staff orientation and knowledge transfer

# Optional Managed IT Services

LANZAR can provide ongoing support through a monthly service agreement, including:

- Remote monitoring

- Software and security updates

- Backup monitoring

- Priority technical support

- Preventative maintenance

- Quarterly infrastructure reviews

- Remote troubleshooting

# Assumptions

This proposal assumes:

- Existing hardware is functional unless otherwise noted during assessment.

- Internet service is available and adequate for cloud integration.

- Any additional hardware or software licensing required beyond the current environment will be quoted separately.

- Project scheduling will be coordinated with library staff to minimize operational disruption.

# Pricing

LANZAR provides professional IT consulting and implementation services at the following rate:

| Service | Rate |
| --- | --- |
| IT Consulting & Infrastructure Services | $89.00/hour |

Services billed at the standard hourly rate include:

- Infrastructure assessment

- Network design and implementation

- Server installation and configuration

- Cloud storage integration

- Data migration

- Security configuration

- System testing

- Documentation

- Staff orientation and training

- Post-deployment support

Additional hardware, software licensing, cloud service subscriptions, or third-party products required for the project will be quoted separately and are not included in the hourly service rate.

# Why LANZAR

LANZAR specializes in practical, scalable technology solutions for organizations that need reliable infrastructure without unnecessary complexity. Our approach emphasizes thoughtful planning, transparent communication, and long-term maintainability. Every deployment is designed with security, documentation, and future growth in mind, ensuring the technology continues to serve the organization well beyond the initial implementation.

# Acceptance

Upon approval, LANZAR will coordinate a detailed site assessment and project schedule with library staff to begin implementation.

Accepted By:

Signature: ________________________________________________ Date: ____________________

Name (Print):

Prepared By:

Signature: ________________________________________________ Date: ____________________

Jonathan Scott

Founder & IT Consultant

LANZAR IT

https://it.lanzar.me